## Sheet1
DAY -1 ( 20-10-21 ) MODULE - Super Dashboard , Dashboard
S.No | Error | For Reference | Module Name | Client Status | Date Posted | Developer Status | Date Updated | Developer Response
project reference : https://docs.google.com/presentation/d/1uHTMKCPU6GmhG4W9BNHkdSpZ2up0oau6/edit#slide=id.gee47088421_0_86 Module reference : https://docs.google.com/document/d/1usf9uJEEVuAtUZoFUY1xBANwqHFYa-LN/edit?usp=sharing&ouid=113719605304752032175&rtpof=true&sd=true Xd reference : https://docs.google.com/document/d/1usf9uJEEVuAtUZoFUY1xBANwqHFYa-LN/edit?usp=sharing&ouid=113719605304752032175&rtpof=true&sd=true
Super Dashboard
1 | Home Page a). Features Dashboard (Infographic ), Class Management, b). Section Management, Subject Management, Teacher Management have to be placed inside School Dashboard |  | Admin Panel | Pending | 2021-10-20 | Pending
2 | Add School Active / Inactive and Delete options are not working for schools login |  | Admin Panel | Pending | 2021-10-20 | Pending
3 | view school verification and validation have not been done for add school form |  | Admin Panel | Pending | 2021-10-20 | Pending
4 | Setting option is missing to change username and password, email, etc for master dashboard |  | Admin Panel | Pending | 2021-10-25 | Pending
5 | Login Form Avail visible option for all logins (chrome does not support ) |  | Admin Panel | Pending | 2021-10-20 | completed | 2021-10-24 | We have completed this point on 24th of October
6 | Home page a). infographic has to be applied for total number of students, total number of staff and overall fee collected b). "more info" for total number of students should be listed with all students according to the selection of class and section with pdf c). "more info" for total number of staff should be listed with staff according to the selection of teaching or non teaching d). "more info" for overall fee should be listed all students according to the selection of class and section as paid or not paid with pdf |  | Admin Panel | Pending | 2021-10-20 | Pending
4 | Assign class management change the title to subject allocation |  | Admin Panel | Pending | 2021-10-20 | Pending
5 | a). Period Management b). complete the form likely c). get class -> get section -> get day-> get period-> get subject-> get teacher |  | Admin Panel | Pending | 2021-10-20 | Pending
7 | Teacher Management a). Form has not been verified and validated b). It adds default address if left empty c). Type View/ Edit instead of view new teacher d). Delete option is not working e). Teacher login is not working on web and apk |  | Admin Panel | Pending | 2021-10-20 | Pending
8 | Student Management a). Form has not been verified and validated b). Parent's email id have to be asked for parent login c). It adds default address if left empty d). Pincode ( Mandatory Symbol missing ) e). Type View/ Edit instead of view new student f). Delete option is not working g). Student login is not working on web and apk |  | Admin Panel | Pending | 2021-10-20 | Pending
9 | Post Management a). Post was not filtered class wise, teaching / non teaching , etc kindly go through the mobile prototype for clarity b). post has to be reviewed by HOD before airing c). Optional Like / Comment field was not added d). Type View/ Edit instead of view new post e). Delete option is not working |  | Admin Panel | Pending | 2021-10-20 | Pending
10 | Non Teaching Staff Management Form is missing | https://docs.google.com/document/d/1usf9uJEEVuAtUZoFUY1xBANwqHFYa-LN/edit?usp=sharing&ouid=113719605304752032175&rtpof=true&sd=true | Admin Panel | Pending | 2021-10-20 | Pending
11 | HOD 's Review Post Form is missing |  | Admin Panel | Pending | 2021-10-20 | Pending
Mobile App
1 | Loading page was not animated |  | Mobile App | Pending | 2021-10-20 | Pending
2 | Teacher, Student, Parent Logins are not working | https://docs.google.com/document/d/1usf9uJEEVuAtUZoFUY1xBANwqHFYa-LN/edit?usp=sharing&ouid=113719605304752032175&rtpof=true&sd=true | Mobile App | Pending | 2021-10-20 | Pending
3 | Logout Missing |  | Mobile App | Pending | 2021-10-20 | Pending
4 | change apk icon from flutter to AHA | https://drive.google.com/file/d/1I5Vx9mIPs5FmwnsGXMoloKoRth72R-b_/view?usp=sharing | Mobile App | Pending | 2021-10-25 | Pending
5 | font type and color code was not followed as we mentioned in XD |  | Mobile App | Pending | 2021-10-25 | Pending
6 | App loading page : seamless texture background is missing on loading page | https://drive.google.com/file/d/11l4UE1nGRf91coTM2llyGbfx59EAfg3m/view?usp=sharing | Mobile App | Pending | 2021-10-25 | Pending
7 | icons are not placed for respective pages to the whole app including menu window |  | Mobile App | Pending | 2021-10-25 | Pending
8 | Login Page : bottom curve design is missing | https://drive.google.com/file/d/1BOGdWOtPDZLJVwicy7SG6OkLJqJQuOeK/view?usp=sharing | Mobile App | Pending | 2021-10-25 | Pending
9 | Login Page : Parent and Non Teaching staff logins are missing | https://docs.google.com/document/d/1usf9uJEEVuAtUZoFUY1xBANwqHFYa-LN/edit?usp=sharing&ouid=113719605304752032175&rtpof=true&sd=true | Mobile App | Pending | 2021-10-25 | Pending
10 | menu has to varied according to the users likely admin, teacher, student, parent, non teaching. it shows same menu for all |  | Mobile App | Pending | 2021-10-25 | Pending
11 | News feed : posts posting from mobile app has not been shown on newsfeed but shows successful msg |  | Mobile App | Pending | 2021-10-25 | Pending
12 | saved posts is not working but shows successfull msg |  | Mobile App | Pending | 2021-10-25 | Pending
13 | app bar and footer bar icons are not designed as shown on prototype | https://drive.google.com/file/d/1xgVRTgeHRJ8L6lW69yTnlIA9xqEJUcSy/view?usp=sharing | Mobile App | Pending | 2021-10-25 | Pending
14 | create post was not designed with filterations, optional comments and like as mentioned on prototype | https://drive.google.com/file/d/1SR8DVNgTxv8zv7NUi9nzehTEJ2081-x8/view?usp=sharing | Mobile App | Pending | 2021-10-25 | Pending
Pending
Pending
Pending
Pending
Pending